## Sheet1
Event Name
Event Date | Timeline | Item | Owner
#VALUE! | 1 year out | Define event date/time
#VALUE! | 1 year out | Define event partners
#VALUE! | 1 year out | Define goals (# of attendees, learning objectives, outputs/outcomes)
#VALUE! | 1 year out | Define concept statement/description
#VALUE! | 1 year out | Define budget
#VALUE! | 1 year out | Define target audience
#VALUE! | 1 year out | Identify potential sponsors secure letters of intent
#VALUE! | 10 months out | Define event city
#VALUE! | 10 months out | Define event venue
#VALUE! | 10 months out | Begin venue contract process
#VALUE! | 10 months out | Finalize event title
#VALUE! | 10 months out | Build & test registration platform
#VALUE! | 10 months out | Begin sponsor contract negotiation and execution
#VALUE! | 8 months out | Go/no-go date dependent upon required sponsorship
#VALUE! | 8 months out | Venue contract finalized
#VALUE! | 8 months out | Draft event webpage
#VALUE! | 8 months out | Draft Communications plan for review and scheduling
#VALUE! | 8 months out | Review draft Communications plan to schedule and finalize
#VALUE! | 8 months out | Return finalized Communications plan with dates
#VALUE! | 6 months out | Webpage live
#VALUE! | 6 months out | Registration opens
#VALUE! | 6 months out | Begin catering contract
#VALUE! | 6 months out | Begin A/V contract
#VALUE! | 6 months out | Finalize keynotes and speakers, get information and headshot
#VALUE! | 6 months out | Begin sending registration updates to stakeholders/partners
#VALUE! | 6 months out | Send registration email blast
#VALUE! | 6 months out | Promote via twitter and facebook
#VALUE! | 4 months out | A/V contract finalized
#VALUE! | 4 months out | Catering contract finalized
#VALUE! | 4 months out | Determine event supply needs
#VALUE! | 4 months out | Obtain contact information for keynote speakers
#VALUE! | 4 months out | Reach out to keynote speakers to collect: speaker LOA and reimbursement forms
#VALUE! | 4 months out | Finalize agenda: breakout activities, sessions, panels, sponsorship slot
#VALUE! | 4 months out | Send agenda to stakeholders/partners
#VALUE! | 3 months out | Send registration reminder email
#VALUE! | 3 months out | Promote via twitter and facebook
#VALUE! | 2 months out | Send "last chance to register" email
#VALUE! | 2 months out | Promote via twitter and facebook
#VALUE! | 2 months out | Request any sponsorship materials from the sponsor
#VALUE! | 1 month out | Registration closes
#VALUE! | 1 month out | Order event supplies
#VALUE! | 1 month out | Update event webpage with "registration closed" language
#VALUE! | 1 month out | Provide final list of attendees to stakeholders/partners
#VALUE! | 1 month out | Design and print name badges
#VALUE! | 1 month out | Forward sponsorship materials
#VALUE! | 2 weeks out | Create staffing plan and run of show
#VALUE! | 2 weeks out | Send run of show to venue and partners
#VALUE! | 2 weeks out | Send final headcount and allergy info to the caterer/venue
#VALUE! | 2 weeks out | Organize pre-con walk thru of the space
#VALUE! | 1 week out | Send "Know Before You Go" email
#VALUE! | 1 day out | Ensure that all materials are at the site
#VALUE! | 1 day out | Walk thru of space
Event Date | Day of | Speakers arrive early to test A/V
Event Date | Day of | Space set-up (arrange welcome table, set out materials)
Event Date | Day of | Run check-in/manage logistics
#VALUE! | 1 day post | Send post-event email (follow up, resources, evaluation etc.)
#VALUE! | 1 week post | Thank you to sponsors
#VALUE! | 1 week post | Thank you to venue
#VALUE! | 1 week post | Thank you to partners
#VALUE! | 1 week post | Schedule post-event debrief
#VALUE! | 1 week post | Post event-debrief
#VALUE! | 1 week post | Process reimbursements
#VALUE! | 1 month post | Collect and summarize evaluation results
#VALUE! | 1 month post | Finalize event outputs
#VALUE! | 1 month post | Disseminate event outpits